## Tabellenblatt1
Tätigkeit | Detailbeschreibung | Aufwand in Stunden | Datum
Meeting | Sprint Review 0 | 1 | 2023-03-17
Meeting | Sprint Review 0 | 1 | 2023-03-17
Meeting | Sprint Review 0 | 1 | 2023-03-17
Meeting | Sprint Review 0 | 1 | 2023-03-17
Meeting | Sprint Review 0 | 1 | 2023-03-17
Projekt Management | Projektplanung | 2 | 2023-03-21
Projekt Management | Projektplanung | 2 | 2023-03-21
Projekt Management | Projektplanung | 2 | 2023-03-21
Projekt Management | Projektplanung | 2 | 2023-03-21
Projekt Management | Projektplanung | 2 | 2023-03-21
Projekt Management | Effort Estimation | 2 | 2023-03-21
Meeting | Effort Estimation | 1 | 2023-03-24
Meeting | Effort Estimation | 1 | 2023-03-24
Meeting | Effort Estimation | 1 | 2023-03-24
Meeting | Effort Estimation | 1 | 2023-03-24
Meeting | Effort Estimation | 1 | 2023-03-24
Backend | Datenbankkonzept | 1 | 2023-03-24
Backend | Datenbankkonzept + ERM | 2 | 2023-03-25
Backend | Überlegungen zu Ordner-Struktur, Django Recherche (Views, Models) | 2 | 2023-03-25
Engine | Recherche + Tutorial zu Pixi.js / Matter.js | 6 | 2023-03-26
Frontend | Design Vorlage Index.html mit Figma erstellen | 2 | 2023-03-26
Backend | Django Recherche (Allgemein) | 2 | 2023-03-28
Backend | Django Recherdche (Allgemein) | 2 | 2023-03-29
Backend | Django Rercherche (User Authentication) | 2 | 2023-04-02
Backend | Erstellung Ordner-Struktur, Login, Django-Recherche (Allgemein) | 4 | 2023-04-04
Frontend | Head, Sidebar, Navbar Bausteine (reusables) | 3 | 2023-04-04
Frontend | Head, Sidebar, Navbar Bausteine (reusables) | 3 | 2023-04-04
Backend | Einbindung von JS, CSS Bibliotheken, Recherche zu & Einbindung einer API | 5 | 2023-04-04
Backend | Nutzer Registrierung | 2 | 2023-04-04
Engine | Recherche + Tutorial zu Pixi.js | 2 | 2023-04-09
Projekt Management | Vorbereitung Sprint | 1 | 2023-04-10
Projekt Management | Sprint 2 | 1 | 2023-04-11
Projekt Management | Sprint Nachbereitung + Git Hub Overview + Django | 2 | 2023-04-11
Projekt Management | Besprechung Team Engine (mit Laurin) | 1 | 2023-04-11
Projekt Management | Sprint Nachbereitung + Git Hub Overview + Django | 2 | 2023-04-11
Projekt Management | Sprint Nachbereitung + Git Hub Overview | 1 | 2023-04-11
Projekt Management | Sprint 2 | 1 | 2023-04-11
Backend | Documentation, bessere Beispieldateien | 2 | 2023-04-19
Engine | Basis Engine Features | 6 | 2023-04-20
Engine | Basic Engine Features | 6 | 2023-04-20
Engine | Advanced Engine Feaures | 2 | 2023-04-21
Engine | Advanced Engine Feaures | 2 | 2023-04-21
Engine | Examples | 4 | 2023-04-21
Frontend | Canvas Element Prototyping | 4 | 2023-04-23
Frontend | Canvas Element Prototyping | 4 | 2023-04-23
Projekt Management | Meeting Sprint 3 + Sprint Nachbereitung | 2 | 2023-04-25
Projekt Management | Meeting Sprint 3 | 1 | 2023-04-25
Projekt Management | Meeting Sprint 3 | 1 | 2023-04-25
Projekt Management | Meeting Sprint 3 | 1 | 2023-04-25
Projekt Management | Meeting Sprint 3 | 1 | 2023-04-25
Engine | Animation Switch Examples | 6 | 2023-04-27
Engine | Animation Switch Examples | 6 | 2023-04-27
Engine | Animation Switch Examples | 2 | 2023-04-28
Engine | Statemachines | 5 | 2023-04-29
Projekt Management | Vorbereitung Technical Review | 2 | 2023-05-03
Projekt Management | Vorbereitung Technical Review | 2 | 2023-05-03
Projekt Management | Vorbereitung Technical Review | 2 | 2023-05-03
Projekt Management | Vorbereitung Technical Review | 2 | 2023-05-03
Projekt Management | Vorbereitung Technical Review | 2 | 2023-05-03
Frontend/Backend | Einlesen in Django | 2 | 2023-05-07
Engine | UML Diagramm/ Code Besprechung mit Teamkollgen | 2 | 2023-05-07
Frontend/Backend | Connecting Django with existing Frontend | 2 | 2023-05-07
Frontend/Backend | Connecting Django with existing Frontend | 2 | 2023-05-07
Frontend/Engine | Debugging in Django Structure | 1 | 2023-05-08
Frontend/Engine | Debugging in Django Structure | 1 | 2023-05-08
Frontend/Engine | Debugging in Django Structure | 1 | 2023-05-08
Frontend/Engine | Debugging in Django Structure | 1 | 2023-05-08
Projekt Management | Meeting Sprint 4 | 1 | 2023-05-09
Projekt Management | Meeting Sprint 4 | 1 | 2023-05-09
Projekt Management | Meeting Sprint 4 | 1 | 2023-05-09
Projekt Management | Meeting Sprint 4 | 1 | 2023-05-09
Projekt Management | Meeting Sprint 4 | 1 | 2023-05-09
Engine | Noodle Charakter/Animationen erstellt | 1 | 2023-05-10
Projekt Management | Brainstorming -> erste Spiele | 1 | 2023-05-10
Projekt Management | Brainstorming -> erste Spiele | 1 | 2023-05-10
Projekt Management | Brainstorming -> erste Spiele | 1 | 2023-05-10
Projekt Management | Brainstorming -> erste Spiele | 1 | 2023-05-10
Projekt Management | Brainstorming -> erste Spiele | 1 | 2023-05-10
Frontend | HTML / CSS for Login and Registration pages + URL-routing | 1 | 2023-05-10
Game Design | Creating "Flappy Farfalle" prototype | 5 | 2023-05-11
Game Design | Creating "Noodle Jump" prototype | 5 | 2023-05-11
Game Design | Creating "Noodle Jump" prototype | 5 | 2023-05-11
Game Design | Creating "Flappy Farfalle" prototype | 5 | 2023-05-11
Game Design | Creating "Noodle Jump" prototype | 5 | 2023-05-11
Projekt Management | Sprint Nachbereitung - Sprint Review Erstellung (Sprint 4) | 1 | 2023-05-15
Game Design | Creating "Noodle Jump" prototype | 4 | 2023-05-20
Game Design | Creating "Noodle Jump" prototype | 4 | 2023-05-20
Game Design | Creating "Noodle Jump" prototype | 4 | 2023-05-20
Game Design | Vertical scrolling, Player controller | 3 | 2023-05-26
Game Design | Vertical scrolling, Player controller | 3 | 2023-05-26
Frontend Design | Trial and Error mit CSS | 3 | 2023-05-31
Game Design | Flappy Farfalle | 4 | 2023-06-01
Game Design | Flappy Farfalle | 4 | 2023-06-01
Frontend Design | Routing, Login, Contact, basics zu profile | 4 | 2023-06-01
Game Design | Flappy Farfalle | 2 | 2023-06-01
Game Design | Noodle Jump, new platform spawning | 5 | 2023-06-04
Game Design | Noodle Jump, new platform spawning | 5 | 2023-06-04
Organisation | GitHub cleanup / merges | 1 | 2023-06-05
Backend | Backend Profil Implementation + Achievement API Recherche | 2 | 2023-06-05
Game Design | Flappy Farfalle - Startscreen/UI | 3 | 2023-06-05
Projekt Management | Meeting Sprint 5 | 1 | 2023-06-05
Projekt Management | Meeting Sprint 5 | 1 | 2023-06-05
Projekt Management | Meeting Sprint 5 | 1 | 2023-06-05
Projekt Management | Meeting Sprint 5 | 1 | 2023-06-05
Projekt Management | Meeting Sprint 5 | 1 | 2023-06-05
Game Design | Flappy Farfalle - UI/Polishing | 3 | 2023-06-05
Game Design | Creating Sprites for Both Games | 4 | 2023-06-06
Polishing | NoodleJump | 4 | 2023-06-07
Polishing | NoodleJump | 4 | 2023-06-07
Polishing | NoodleJump | 3 | 2023-06-07
Backend | Achievements + API | 2 | 2023-06-10
Backend | Nutzerprofil | 1 | 2023-06-11
Artwork | Rockin Ramen | 5 | 2023-06-15
Polishing | NoodleJump + UI | 5 | 2023-06-15
Polishing | NoodleJump + UI | 5 | 2023-06-15
Polishing | Rockin Ramen (NoodleJump/FlappyFarfalla) | 5 | 2023-06-15
Artwork | The Joe Rockan | 1 | 2023-06-15
Projekt Management | Sprint 5 + Sprint 6 Nachbereitung | 2 | 2023-06-13
Game Design | Particles Installation | 5 | 2023-06-18
Merge/Polish | GitHub cleanup / merges, PagePolish | 3 | 2023-06-18
Merge/Polish | GitHub cleanup / merges, PagePolish | 3 | 2023-06-18
Merge/Polish | GitHub cleanup / merges, PagePolish | 3 | 2023-06-18
Merge/Polish | GitHub cleanup / merges, PagePolish | 3 | 2023-06-18
Merge/Polish | GitHub cleanup / merges, PagePolish | 3 | 2023-06-18
Game Design | Particles Demo | 3 | 2023-06-18
Polishing | Particles Demo | 2 | 2023-06-19
Polishing | Soundeffects | 2 | 2023-06-19
Rubberducking | Mentale und Technische Unterstützung | 2 | 2023-06-19
Projekt Management | Meeting Sprint 6 | 1 | 2023-06-19
Projekt Management | Meeting Sprint 6 | 1 | 2023-06-19
Projekt Management | Meeting Sprint 6 | 1 | 2023-06-19
Projekt Management | Meeting Sprint 6 | 1 | 2023-06-19
Backend | Implementierung: Achievements, Achievement API, Profile; polish Login & Registrierung | 4 | 2023-06-21
Projekt Management | Presentation Planning | 5 | 2023-06-26
Projekt Management | Presentation Planning | 5 | 2023-06-26
Projekt Management | Presentation Planning | 5 | 2023-06-26
Projekt Management | Presentation Planning | 5 | 2023-06-26
Projekt Management | Presentation Planning | 5 | 2023-06-26
30